## Buyer Transaction Checklist
TLSA GROUP RESOURCES |  |  | COMPLIMENTARY TRANSACTION TOOL
BUYER TRANSACTION CHECKLIST
A practical contract-to-close management tool for real estate professionals
TRANSACTION INFORMATION
AGENT / REALTOR |  | BUYER(S)
PROPERTY ADDRESS |  |  | TITLE COMPANY
CONTRACT DATE |  | OPTION / DUE DILIGENCE END | CLOSING DATE
DONE | TASK | TIMING / TRIGGER | STATUS | NOTES
1. CONTRACT INTAKE
☐ | Review executed contract and all applicable addenda/disclosures. | At receipt | Not Started
☐ | Record all critical dates and special terms, including deposits, option/due diligence, financing, appraisal, survey, closing, possession, and other deadlines. | At receipt | Not Started
☐ | Verify buyer, property, seller/co-op agent, title, lender, and brokerage contact information. | At receipt | Not Started
☐ | Confirm title has the complete contract package and buyer contact information. | Within 1 business day | Not Started
☐ | Confirm earnest money and option/due-diligence funds have been delivered or their status verified with the appropriate party. | By contract deadline | Not Started
☐ | Confirm lender/loan officer information and that the buyer has completed required loan-application steps when financing is involved. | Early contract period | Not Started
☐ | Confirm closing date and preliminary closing arrangements with title and buyer. | Early contract period | Not Started
2. DUE DILIGENCE & INSPECTIONS
☐ | Coordinate inspection scheduling and property access with the appropriate parties. | As soon as practical | Not Started
☐ | Track inspection completion and the option/due-diligence deadline. | During due diligence | Not Started
☐ | Track repair negotiations, credits, or other buyer decisions and ensure approved amendments are fully executed. | During due diligence | Not Started
☐ | Distribute fully executed amendments to title, lender, and applicable parties. | Upon execution | Not Started
☐ | Confirm option/due-diligence period expiration and note any remaining obligations. | At period end | Not Started
3. FINANCING & CONTRACT-TO-CLOSE
☐ | Maintain recurring status follow-up with title, lender, and co-op agent. | Weekly until close | Not Started
☐ | Track appraisal order, appointment, completion, and any resulting transaction action. | Per lender timeline | Not Started
☐ | Track survey requirements/order and follow up on delays or title/underwriting issues. | Until resolved | Not Started
☐ | Track HOA/subdivision/resale certificate documents when applicable. | Until received | Not Started
☐ | Monitor title commitment/preliminary title report and route buyer questions or title issues to the appropriate professionals. | Until clear | Not Started
☐ | Track buyer financing milestones and financing-contingency deadlines; flag approaching or missed dates. | Per contract | Not Started
☐ | Confirm homeowner's insurance is arranged and lender-required insurance information has been provided when applicable. | Before lender deadline | Not Started
☐ | Track agreed repairs and collect receipts/documentation required by contract when applicable. | Before closing | Not Started
☐ | Confirm buyer responds promptly to lender, title, insurance, and other transaction requests. | Ongoing | Not Started
☐ | Track special provisions, non-realty items, possession terms, and other contract-specific buyer obligations. | Ongoing | Not Started
4. PRE-CLOSING
☐ | Confirm clear-to-close status with lender when financing is involved. | Before closing | Not Started
☐ | Confirm buyer closing disclosure has been issued when applicable and required review periods are on track. | Before closing | Not Started
☐ | Confirm final walkthrough is scheduled and buyer understands its purpose. | Before closing | Not Started
☐ | Confirm agreed repairs or other pre-closing property obligations are complete or appropriately documented. | Before walkthrough | Not Started
☐ | Confirm closing date, time, location, or signing method with buyer and title. | 1–2 weeks / before closing | Not Started
☐ | Remind buyer to bring acceptable identification and follow title-specific signing requirements. | Before closing | Not Started
☐ | Confirm buyer has received required funds/wiring instructions directly from the appropriate trusted party and understands that wire instructions should be independently verified before sending funds. | Before sending funds | Not Started
☐ | Coordinate keys, remotes, mailbox keys, access devices, utilities, and possession arrangements as applicable. | Before closing | Not Started
☐ | Review unresolved items and confirm the transaction is ready for closing. | 24 hours before closing | Not Started
5. CLOSING & FUNDING
☐ | Monitor signing/closing completion and funding status. | Closing day | Not Started
☐ | Confirm funding/closing before communicating completion or coordinating possession when required by the contract/title instructions. | Upon funding / closing | Not Started
☐ | Coordinate key/access delivery based on possession terms. | After funding / per contract | Not Started
☐ | Provide buyer with appropriate final transaction information and confirm any immediate post-closing handoff items. | After closing | Not Started
6. POST-CLOSING
☐ | Update CRM/transaction-management status according to brokerage requirements. | After funding | Not Started
☐ | Complete/upload required brokerage compliance documents and verify the file is complete. | After funding | Not Started
☐ | Record final funding/closing date and archive transaction documents according to brokerage procedure. | After funding | Not Started
☐ | If leaseback/temporary possession applies, calendar the expiration and possession/key handoff. | Before expiration | Not Started
☐ | Confirm commission/payment milestone according to brokerage procedure. | After funding | Not Started
Complimentary resource provided by TLSA Group LLC
© 2026 TLSA Group LLC. All rights reserved. ¦ This checklist is a transaction-management aid and does not replace the executed contract, brokerage requirements, or professional judgment. Contract terms and deadlines control. Real estate professionals remain responsible for licensed advice, negotiation, strategy, approvals, and applicable compliance.

## How to Use
TLSA GROUP RESOURCES ¦ BUYER TRANSACTION CHECKLIST
HOW TO USE
Enter the transaction information in the highlighted cells. During the transaction, use the Done dropdown (☐ / ✓), Status dropdown, and Notes column. Completing a task with ✓ shades the row for quick visual tracking. Those working cells are unlocked; the checklist structure and task language are protected.
Use the highlighted cells to record the transaction details. Keep this copy for your own work, and check the contract and your brokerage procedures for the deadlines that apply.
Complimentary resource provided by TLSA Group LLC for real estate professionals. The checklist is a planning aid; the executed contract, brokerage requirements, and professional judgment control.
© 2026 TLSA Group LLC. All rights reserved.