## Seller Transaction Checklist
TLSA GROUP RESOURCES |  |  | COMPLIMENTARY TRANSACTION TOOL
SELLER TRANSACTION CHECKLIST
A practical contract-to-close management tool for real estate professionals
TRANSACTION INFORMATION
AGENT / REALTOR |  | SELLER(S)
PROPERTY ADDRESS |  |  | TITLE COMPANY
CONTRACT DATE |  | OPTION END | CLOSING DATE
DONE | TASK | TIMING / TRIGGER | STATUS | NOTES
1. CONTRACT INTAKE
☐ | Review executed contract and all applicable addenda/disclosures. | At receipt | Not Started
☐ | Record all critical dates and special terms, including option, deposits, survey, financing, appraisal, closing, possession/leaseback, and other deadlines. | At receipt | Not Started
☐ | Verify seller, property, co-op agent, title, lender (if applicable), and brokerage contact information. | At receipt | Not Started
☐ | Confirm title has the complete contract package and seller contact information. | Within 1 business day | Not Started
☐ | Confirm earnest money and option fee receipt/status with title or appropriate party. | By contract deadline | Not Started
☐ | Confirm existing survey and affidavit/T-47 status; determine whether a new survey is required. | Early contract period | Not Started
☐ | Confirm closing date and preliminary closing arrangements with title and seller. | Early contract period | Not Started
2. OPTION & INSPECTIONS
☐ | Confirm seller is aware of scheduled inspections and access requirements. | When scheduled | Not Started
☐ | Track inspection completion and any repair request or amendment from the buyer side. | During option period | Not Started
☐ | Track repair negotiations/decisions and ensure approved amendments are fully executed. | During option period | Not Started
☐ | Distribute fully executed amendments to title, lender, and applicable parties. | Upon execution | Not Started
☐ | Confirm option period expiration and note any remaining obligations. | At option end | Not Started
3. CONTRACT-TO-CLOSE
☐ | Maintain recurring status follow-up with title, lender, and co-op agent. | Weekly until close | Not Started
☐ | Track survey order/acceptance and follow up on delays or title/underwriting issues. | Until resolved | Not Started
☐ | Track HOA/subdivision/resale certificate documents when applicable. | Until received | Not Started
☐ | Confirm seller information form and title-requested seller documents have been provided. | Early contract period | Not Started
☐ | Track appraisal order, appointment, completion, and any resulting transaction action. | Per lender timeline | Not Started
☐ | Track title commitment and open title requirements until resolved. | Until clear | Not Started
☐ | Track repair completion and collect receipts/documentation required by contract. | Before closing | Not Started
☐ | Track financing contingency and lender milestones; flag approaching or missed deadlines. | Per contract | Not Started
☐ | Track CDA/commission disbursement authorization according to brokerage procedure. | Before closing | Not Started
☐ | Track special provisions, exclusions, non-realty items, possession/leaseback, and other contract-specific obligations. | Ongoing | Not Started
4. PRE-CLOSING
☐ | Confirm clear-to-close status with lender when financing is involved. | Before closing | Not Started
☐ | Confirm buyer closing disclosure has been issued when applicable. | Before closing | Not Started
☐ | Obtain seller settlement statement/closing disclosure and review known transaction figures. | Before closing | Not Started
☐ | Confirm contract credits, repair credits, commissions, and other known terms appear correctly; route discrepancies for correction. | Before closing | Not Started
☐ | Confirm final walkthrough schedule and seller awareness. | Before closing | Not Started
☐ | Coordinate keys, remotes, mailbox keys, access devices, and possession instructions. | Before closing | Not Started
☐ | Confirm closing location, date, time, identification, funds/wiring instructions, and title-specific requirements with seller. | 1–2 weeks / before closing | Not Started
☐ | Confirm title has required closing documents and instructions ready. | Day before / day of | Not Started
☐ | Review unresolved items and confirm the transaction is ready for closing. | 24 hours before closing | Not Started
5. CLOSING & FUNDING
☐ | Monitor signing/closing completion and funding status. | Closing day | Not Started
☐ | Confirm funding before communicating completion or releasing keys when required by the contract/title instructions. | Upon funding | Not Started
☐ | Coordinate key/access transfer based on possession terms. | After funding / per contract | Not Started
☐ | Confirm sign, lockbox/Supra, and other listing closeout actions are completed. | After closing | Not Started
6. POST-CLOSING
☐ | Update MLS/CRM/transaction-management status according to brokerage requirements. | After funding | Not Started
☐ | Complete/upload required brokerage compliance documents and verify the file is complete. | After funding | Not Started
☐ | Record final funding/closing date and archive transaction documents according to brokerage procedure. | After funding | Not Started
☐ | If leaseback/temporary possession applies, calendar the expiration and possession/key handoff. | Before expiration | Not Started
☐ | Confirm commission/payment milestone according to brokerage procedure. | After funding | Not Started
Complimentary resource provided by TLSA Group LLC
© 2026 TLSA Group LLC. All rights reserved. ¦ This checklist is a transaction-management aid and does not replace the executed contract, brokerage requirements, or professional judgment. Contract terms and deadlines control. Real estate professionals remain responsible for licensed advice, negotiation, strategy, approvals, and applicable compliance.

## How to Use
TLSA GROUP RESOURCES ¦ SELLER TRANSACTION CHECKLIST
HOW TO USE
Enter the transaction information in the highlighted cells. During the transaction, use the Done dropdown (☐ / ✓), Status dropdown, and Notes column. Completing a task with ✓ shades the row for quick visual tracking. Those working cells are unlocked; the checklist structure and task language are protected.
Use the highlighted cells to record the transaction details. Keep this copy for your own work, and check the contract and your brokerage procedures for the deadlines that apply.
Complimentary resource provided by TLSA Group LLC for real estate professionals. The checklist is a planning aid; the executed contract, brokerage requirements, and professional judgment control.
© 2026 TLSA Group LLC. All rights reserved.